## Project
Traceability Matrix Project: VitalNest Wellness Website Relaunch Date: 1 March 20xx
Requirement ID | Requirement Type | Requirement Description | Source / Stakeholder | Business Objective / Goal | Acceptance Criteria | Linked Functional / Non-Functional Requirement | Owner | Priority | Status | Verification Method | Related Risks | Comments / Notes
REQ-001 | Functional | Redesign product catalog with enhanced filtering options | Marketing Lead | Improve customer browsing experience | Product catalog is functional with at least 5 filter options | REQ-004 | Marketing Lead | High | In Progress | UAT Testing | Customer resistance to change | Filters should include categories, price, and ratings
REQ-002 | Functional | Implement subscription service for high-demand products | CEO (Project Sponsor) | Increase customer retention through subscriptions | Subscription service allows customers to opt-in and manage plans | REQ-004 | Web Development Vendor | High | In Progress | UAT Testing | Delays with external vendor | Subscription limited to select products initially
REQ-003 | Non-Functional | Ensure seamless data migration from the old website | IT Manager | Avoid disruption during transition to new site | All data is migrated without loss or errors | None | IT Manager | Medium | Not Started | Data Migration Tests | Data migration issues | Ensure data security throughout migration
REQ-004 | Functional | Develop personalized dashboard for order tracking and subscription management | Customer Representative | Provide better user experience and customer control | Dashboard accurately displays orders and subscription status | REQ-001, REQ-002 | Customer Representative | High | In Progress | UAT and Customer Feedback | Technical integration issues | Interdependencies require close monitoring

## Instructions
Traceability Matrix Completion Instructions
Entry | Instruction | Example
Project Name | Mention the project or program name for context. | Secure Retail System Upgrade
Requirement ID | Assign a unique identifier to each requirement using sequential numbering. | 001
Requirement Type | Specify if the requirement is Functional or Non-Functional. | Functional
Requirement Description | Provide a clear, concise description of the requirement. | The system shall allow login through biometric authentication.
Source / Stakeholder | Identify where the requirement originated (e.g., stakeholder, workshop). | Operations Manager
Business Objective / Goal | Describe the business need or strategic objective supported by the requirement. | Improve security and user experience
Acceptance Criteria | Define the conditions under which the requirement will be accepted. | User logs in successfully via biometrics
Linked Functional / Non-Functional Requirement | List related or dependent requirements by referencing their IDs. | 003 (Performance)
Owner | Identify the person or team responsible for fulfilling the requirement. | IT Lead
Priority | Assign a priority level (e.g., High, Medium, Low). | High
Status | Track the progress (e.g., Not Started, In Progress, Blocked, Completed). | In Progress
Verification Method | Specify how the requirement will be verified (e.g., Testing, Inspection). | Testing
Related Risks | Identify risks associated with the requirement to assist in planning. | Security breaches
Comments / Notes | Capture additional information or ongoing discussions. | Biometric SDK vendor confirmed.