## Risk Register
Project: Off Site Date: June 19 20XX
# | Cause | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
1 | Vendor | Low Commitment Low Quality Work | Schedule Slips Budget Overages | Vendor Manager | Thereat | 2 | 5 | 10 | Schedule Slips | Careful Source Selection
2 | Work From Home | Productivity Reduced | Daily Workload | HR | Thereat | 2.5 | 3.5 | 8.75 | Missed Deadlines | Working from Home Training
3 | Construction Proximity | Noise Work Disruptions | Lost Productivity | QC | Thereat | 3 | 3 | 9 | Worker Complaints | QC Partition Plans
| Budget | No Constraints | Adequate Resources | Finance | Opportunity | 5 | -5 | -25 | None | Plane Resources carefully
Total Risk Score | [7 empty] | 2.75
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low

## Example
Project: Off Site Date: June 19 20XX
# | Cause | Event | Impact | Risk Owner | Category | Probability Risk Rating | Impact Risk Rating | Risk Score | Trigger | Response
1 | Management Support | 1. Great Event 2. Super Turnout | Increased motivation | Bill | O | 5 | -5 | -25 | High RSVP | 1. Market 2. Prizes
4 | Catering | Late Food Delivery | Delayed events | Food Services | T | 3.5 | 5 | 17.5 | None | Call 1-Day Prior
3 | Multiple Projects | Lack of capacity | Schedule delays | Bill | T | 4 | 4 | 16 | Missed deadlines | Use Staffing Mgt Plan
2 | Bad Weather | 1. Reduced Turnout 2. Late Start | Reduced impact | Jane | T | 3 | 4 | 12 | Weather Report | Ensure inside venue Plan B
Total Risk Score | [7 empty] | 20.5
May use the Project Risk Score: Total Negative scores - positive scores. Larger the gap--the more risk the project has.
|  | Probability Risk Rating |  | Impact Risk Rating
|  | 5: High |  | 5: High
|  | 4: High to Moderate |  | 4: High to Moderate
|  | 3: Moderate |  | 3: Moderate
|  | 2: Moderate to Low |  | 2: Moderate to Low
|  | 1: Low |  | 1: Low